## Task Plan
Engineer | Task | Description | Duration | Start | End | Dependencies | Risk | Deliverable
PHASE 1: FOUNDATION (8:00 – 10:00)
Eng 1 | Database schema & seed data | Design drug inventory schema (drugs, stock_levels, prescriptions, audit_log). Seed with 50+ realistic medicines, quantities, expiry dates. | 2 hrs | 8:00 | 10:00 | None | Low | SQLite DB + seed script
Eng 2 | Orchestrator agent core | Build the central orchestrator: task queue, agent dispatcher, conflict resolution (e.g. two agents claiming same stock). WebSocket event bus. | 2 hrs | 8:00 | 10:00 | None | Med | orchestrator.py + event bus
Eng 3 | Doctor agent | System prompt for clinical persona. Actions: create prescription, check drug availability, request restock. Structured output parsing. | 2 hrs | 8:00 | 10:00 | None | Low | doctor_agent.py
Eng 4 | Stock manager agent | System prompt for warehouse persona. Actions: receive stock, check expiry dates, flag low-stock items, generate reorder alerts. | 2 hrs | 8:00 | 10:00 | None | Low | stock_manager_agent.py
Eng 5 | Dashboard frontend scaffold | React/Streamlit app with layout: stock levels panel, activity feed, alerts panel, audit log. Mock data for now. | 2 hrs | 8:00 | 10:00 | None | Low | dashboard app shell
✓ MILESTONE 1: All components boot independently
PHASE 2: INTEGRATION (10:00 – 13:00)
Eng 1 | Dispenser agent | System prompt for pharmacist persona. Actions: fill prescriptions, deduct stock, log dispensing events. Validates against DB. | 2 hrs | 10:00 | 12:00 | DB schema | Low | dispenser_agent.py
Eng 2 | Agent ↔ orchestrator wiring | Connect all 4 agents to orchestrator. Message format, routing, error handling. Doctor Rx triggers dispenser automatically. | 3 hrs | 10:00 | 13:00 | All agents | High | Integrated pipeline
Eng 3 | Government official agent | System prompt for MoH auditor. Actions: run audit queries, flag anomalies (unusual volumes, expired dispensing), generate compliance report. | 2 hrs | 10:00 | 12:00 | DB schema | Low | gov_agent.py
Eng 4 | Simulation scenario engine | Script that runs a realistic day: 15 prescriptions, 3 stock receipts, 2 expiry alerts, 1 anomaly for the auditor to catch. | 2 hrs | 10:00 | 12:00 | DB + agents | Med | simulation.py
Eng 5 | Dashboard ↔ backend API | Connect dashboard to live data: REST endpoints or WebSocket for real-time stock levels, activity feed, alerts. | 3 hrs | 10:00 | 13:00 | DB + orchestrator | Med | Live dashboard
✓ MILESTONE 2: End-to-end flow works (13:00)
PHASE 3: POLISH & DEMO PREP (14:00 – 17:00)
Eng 1 | Audit trail & reporting | Immutable event log with timestamps. Summary report generation for gov agent. Export to CSV. | 2 hrs | 14:00 | 16:00 | Integrated pipeline | Low | audit_trail.py + reports
Eng 2 | Error handling & resilience | Retry logic, graceful LLM timeout handling, fallback responses. Ensure demo never crashes. | 2 hrs | 14:00 | 16:00 | Integrated pipeline | Med | Hardened system
Eng 3 | Demo scenario scripting | Curated demo flow: doctor prescribes → dispenser fulfills → stock drops → alert fires → auditor flags anomaly. Timed and rehearsed. | 2 hrs | 14:00 | 16:00 | Simulation engine | Low | demo_script.md
Eng 4 | Dashboard visualizations | Stock level bar charts, expiry heatmap, real-time activity ticker, alert badges. Make it visually impressive. | 3 hrs | 14:00 | 17:00 | Live dashboard | Med | Polished dashboard
Eng 5 | Integration testing & fixes | Run full simulation 3+ times. Fix race conditions, UI glitches, agent misbehavior. Buffer for surprises. | 3 hrs | 14:00 | 17:00 | Everything | High | Stable demo
✓ MILESTONE 3: Demo-ready system (17:00)
PHASE 4: REHEARSAL (17:00 – 18:00)
All | Dry run & final fixes | Full team runs the demo end-to-end twice. Fix any last-minute issues. Assign demo presenter and backup. | 1 hr | 17:00 | 18:00 | Everything | Low | Rehearsed demo

## Engineer View
Engineer | Phase 1 (8-10) | Phase 2 (10-13) | Phase 3 (14-17) | Phase 4 (17-18) | Total Tasks
Eng 1 | DB schema & seed data | Dispenser agent | Audit trail & reporting | Dry run | 4
Eng 2 | Orchestrator agent core | Agent ↔ orchestrator wiring | Error handling & resilience | Dry run | 4
Eng 3 | Doctor agent | Government official agent | Demo scenario scripting | Dry run | 4
Eng 4 | Stock manager agent | Simulation scenario engine | Dashboard visualizations | Dry run | 4
Eng 5 | Dashboard frontend scaffold | Dashboard ↔ backend API | Integration testing & fixes | Dry run | 4